Initiated:  May 21, 2026																		Revision:  (Date)

Sponsor:  Ruth Barratt

Future state

- Objective statement: By April 2027, I will publish the Accounting Career Paths Guide to provide students with a deeper understanding of the variety of career paths available in the accounting profession. Accounting majors will feel more confident in their decision to major in accounting, and non-accounting majors will have a more informed view of the profession. I will measure success using the metrics below in addition to student surveys before and after the project is complete.

- Success Metrics: A published Accounting Career Paths Guide, at least three five-minute classroom presentations, at least one industry speaker event

-

Implementation plan

Phase 1 – Planning

- Objectives: Conduct research, identify needs, industry professional and faculty partner initial communications

Phase 2 – Development and Coordination

- Objectives: Prepare Accounting Career Paths Guide, Prepare classroom presentations, Coordinate speaker calendar, coordinate with faculty for classroom visits

Phase 3 – Pilot Launch

- Objectives: Deliver in-class presentations, distribute Accounting Career Paths Guide, host industry speaker(s), facilitate networking opportunities, meet one-on-one with interested students

Phase 4 – Assessment

- Objectives: Evaluate effectiveness of presentations, Accounting Career Paths Guide

Phase 5 – Wrap-Up

- Update Accounting Career Paths Guide based on feedback, expand industry connections

Current condition

- Through conversations I have had with current accounting students, I have realized that current perceptions of accounting careers are relatively limited.

- RSOB is yet to have an accounting major go on to earn their CPA, which suggests students may not fully understand the steps needed to pursue certain accounting career paths (e.g. public accounting).

- When preparing the Accounting Career Paths Guide, I will research what factors are important to students when selecting a career to ensure the guide contains relevant information. I will also research the accounting workforce to ensure the guide is comprehensive.

- This project is supported by conversations with students and faculty.

The problem

- Problem statement:  Current students in the Rader School of Business (“RSOB”) do not have a deep understanding of the accounting career paths available to them.

- In scope:  I will create an Accounting Career Paths Guide, make informative in-class presentations, and host guest speaker events.

- Out of scope:  I will not focus on recruiting accounting majors or job placement.

- Cross-functional dependencies to be considered: I will be dependent on RSOB faculty for input and facilitation of brief classroom presentations. I may also be dependent on non-RSOB advisors to help identify and engage with students who are reconsidering their current major. Lastly, I am dependent on student participation and the availability of industry speakers.

- Key stakeholders and team members:  Project Lead (Alyssa Henke), Faculty, RSOB students, non-RSOB MSOE students, industry speakers, RSOB chair

Steering committee: Alyssa Henke